## Sheet1
Task Mode | WBS | Task Name | Duration | Start | Finish | Predecessors | Resource Names
Auto Scheduled | 0 | FindAGrave-3 Jul 2015- 10 am | 23.75 days | 2015-06-25 10:00 | 2015-08-07 15:00
Auto Scheduled | 1 | 1. Implementing CI in docker container | 7.25 days | 2015-07-01 10:00 | 2015-07-14 15:00
Auto Scheduled | 1.1 | checking latest docker plugins for jenkins | 16 hrs | 2015-07-01 10:00 | 2015-07-06 11:00 |  | Bama
Auto Scheduled | 1.2 | configuring docker plugin with jenkins | 8 hrs | 2015-07-06 11:00 | 2015-07-07 13:00 | 3 | Vishnu
Auto Scheduled | 1.3 | creating docker environment with required configuration through jenkins | 8 hrs | 2015-07-07 14:00 | 2015-07-08 17:00 | 4 | Bama
Auto Scheduled | 1.4 | creating docker environment with required configuration through jenkins | 8 hrs | 2015-07-07 15:00 | 2015-07-08 17:00 | 5FF | Vishnu
Auto Scheduled | 1.5 | running CI job in docker container as a slave | 10 hrs | 2015-07-09 10:00 | 2015-07-10 17:00 | 5 | Bama
Auto Scheduled | 1.6 | running CI job in docker container as a slave | 10 hrs | 2015-07-09 12:00 | 2015-07-10 17:00 | 7FF | Vishnu
Auto Scheduled | 1.7 | Actual implementation at project team CI server. | 8 hrs | 2015-07-13 10:00 | 2015-07-14 15:00 | 7 | Bama
Auto Scheduled | 1.8 | Actual implementation at project team CI server. | 8 hrs | 2015-07-13 12:00 | 2015-07-14 15:00 | 9FF | Vishnu
Auto Scheduled | 1.9 | Milestone : CI | 0 days | 2015-07-14 15:00 | 2015-07-14 15:00 | 10
Auto Scheduled | 2 | 2. Jenkins job for removing existing environment | 2 days | 2015-07-17 11:00 | 2015-07-21 16:00
Auto Scheduled | 2.1 | Working on jenkins job for removing existing environment | 11 hrs | 2015-07-17 11:00 | 2015-07-20 17:00 | 41 | Vaibhav
Auto Scheduled | 2.2 | Working on jenkins job for removing existing environment | 11 hrs | 2015-07-17 11:00 | 2015-07-20 17:00 | 13SS | Vishnu
Auto Scheduled | 2.3 | Review | 4 hrs | 2015-07-21 10:00 | 2015-07-21 16:00 | 14 | Bama
Auto Scheduled | 2.4 | Milestone : Remove existing environment | 0 days | 2015-07-21 16:00 | 2015-07-21 16:00 | 15
Auto Scheduled | 3 | 3. Rollback environment using jenkins | 3.25 days | 2015-07-16 16:00 | 2015-07-23 11:00
Auto Scheduled | 3.1 | Rollback activity of environment | 24 hrs | 2015-07-16 16:00 | 2015-07-22 16:00 | 65 | Puneet
Auto Scheduled | 3.2 | Rollback activity of environment | 8 hrs | 2015-07-21 11:00 | 2015-07-22 16:00 | 18FF | Bama
Auto Scheduled | 3.3 | Review | 2 hrs | 2015-07-22 16:00 | 2015-07-23 11:00 | 19 | Bama
Manually Scheduled | 4 | 4. Create environment for QA | 5 days | 2015-07-03 14:00 | 2015-07-14 11:00
Auto Scheduled | 4.1 | running CD job in docker container as a slave | 6 hrs | 2015-07-03 15:00 | 2015-07-07 11:00 | 23FF | Bama
Auto Scheduled | 4.2 | running CD job in docker container as a slave-For DB | 8 hrs | 2015-07-03 16:00 | 2015-07-07 11:00 | 50 | Jithin
Auto Scheduled | 4.3 | running CD job in docker container as a slave- Will assist all | 8 hrs | 2015-07-03 14:00 | 2015-07-07 11:00 | 23FF | Rajiv
Auto Scheduled | 4.4 | running CD job in docker container as a slave- For Frontend | 8 hrs | 2015-07-03 16:00 | 2015-07-07 11:00 | 23FF | Puneet
Auto Scheduled | 4.5 | running CD job in docker container as a slave- For Backend | 8 hrs | 2015-07-03 16:00 | 2015-07-07 11:00 | 23FF | Navneet
Auto Scheduled | 4.6 | create Docker container from SCM's dockerfile | 4 hrs | 2015-07-07 11:00 | 2015-07-08 11:00 | 24 | Rajiv
Auto Scheduled | 4.7 | create Docker container from SCM's dockerfile | 4 hrs | 2015-07-07 14:00 | 2015-07-08 11:00 | 27FF | Jithin
Auto Scheduled | 4.8 | create Docker container from SCM's dockerfile | 4 hrs | 2015-07-07 14:00 | 2015-07-08 11:00 | 27FF | Puneet
Auto Scheduled | 4.9 | create Docker container from SCM's dockerfile | 4 hrs | 2015-07-07 12:00 | 2015-07-08 11:00 | 27FF | Navneet
Auto Scheduled | 4.1 | Install node, npm, grunt-cli git in container | 10 hrs | 2015-07-08 11:00 | 2015-07-10 11:00 | 27 | Rajiv
Auto Scheduled | 4.11 | Install node, npm, grunt-cli git in container | 10 hrs | 2015-07-08 14:00 | 2015-07-10 11:00 | 31FF | Jithin
Auto Scheduled | 4.12 | Install node, npm, grunt-cli git in container | 10 hrs | 2015-07-08 14:00 | 2015-07-10 11:00 | 31FF | Puneet
Auto Scheduled | 4.13 | Install node, npm, grunt-cli git in container | 10 hrs | 2015-07-06 12:00 | 2015-07-10 11:00 | 31FF | Navneet
Auto Scheduled | 4.14 | connect with existing data base container | 6 hrs | 2015-07-10 11:00 | 2015-07-13 11:00 | 34 | Jithin
Auto Scheduled | 4.15 | Review | 2 hrs | 2015-07-13 11:00 | 2015-07-13 17:00 | 35 | Bama
Auto Scheduled | 4.16 | Milestone : QA environment created | 0 days | 2015-07-13 17:00 | 2015-07-13 17:00 | 36
Auto Scheduled | 5 | 5. Deploy build code to containers | 2.38 days | 2015-07-14 10:00 | 2015-07-17 11:00
Auto Scheduled | 5.1 | Run server for testing the application on QA server | 8 hrs | 2015-07-14 10:00 | 2015-07-15 15:00 | 37 | Bama
Auto Scheduled | 5.2 | Run server for testing the application on QA server | 8 hrs | 2015-07-14 12:00 | 2015-07-15 15:00 | 39FF | Vaibhav
Auto Scheduled | 5.3 | Get IP and Port of the server and send email notification | 8 hrs | 2015-07-15 15:00 | 2015-07-17 11:00 | 39 | Bama
Auto Scheduled | 5.4 | Get IP and Port of the server and send email notification | 8 hrs | 2015-07-15 16:00 | 2015-07-17 11:00 | 41FF | Vaibhav
Auto Scheduled | 6 | 6. Commit docker container and push it to Docker local registry | 14.63 days | 2015-07-02 16:00 | 2015-07-30 12:00
Auto Scheduled | 6.1 | installing docker registry through docker container- client side | 12 hrs | 2015-07-27 11:00 | 2015-07-29 15:00 | 74 | Bama
Auto Scheduled | 6.2 | installing docker registry through docker container- client side | 12 hrs | 2015-07-22 10:00 | 2015-07-29 15:00 | 44FF | Rajiv
Auto Scheduled | 6.3 | installing docker registrythrough docker container- client side | 12 hrs | 2015-07-27 15:00 | 2015-07-29 15:00 | 44FF | Vishnu
Auto Scheduled | 6.4 | docker registry configuration for local docker repo- client side | 4 hrs | 2015-07-29 15:00 | 2015-07-30 12:00 | 45 | Bama
Auto Scheduled | 6.5 | docker registry configuration for local docker repo- client side | 4 hrs | 2015-07-23 12:00 | 2015-07-30 12:00 | 47FF | Rajiv
Auto Scheduled | 6.6 | docker registry configuration for local docker repo- client side | 4 hrs | 2015-07-29 15:00 | 2015-07-30 12:00 | 47FF | Vishnu
Auto Scheduled | 6.7 | Training to Viabhav,Navneet,Rajiv,Puneet,Jithin,Vishnu - Docker with Jenkins operations | 5 hrs | 2015-07-02 16:00 | 2015-07-03 16:00 |  | Bama
Auto Scheduled | 6.8 | Training to Viabhav,Navneet,Rajiv,Puneet,Jithin,Vishnu - Docker with Jenkins operations | 5 hrs | 2015-07-03 10:00 | 2015-07-03 16:00 | 50FF | Vaibhav
Auto Scheduled | 6.9 | Training to Viabhav,Navneet,Rajiv,Puneet,Jithin,Vishnu - Docker with Jenkins operations | 5 hrs | 2015-07-03 10:00 | 2015-07-03 16:00 | 50FF | Vishnu
Auto Scheduled | 6.1 | Training to Viabhav,Navneet,Rajiv,Puneet,Jithin,Vishnu - Docker with Jenkins operations | 5 hrs | 2015-07-03 10:00 | 2015-07-03 16:00 | 50FF | Rajiv
Auto Scheduled | 6.11 | Training to Viabhav,Navneet,Rajiv,Puneet,Jithin,Vishnu - Docker with Jenkins operations | 5 hrs | 2015-07-03 10:00 | 2015-07-03 16:00 | 50FF | Navneet
Auto Scheduled | 6.12 | Training to Viabhav,Navneet,Rajiv,Puneet,Jithin,Vishnu - Docker with Jenkins operations | 5 hrs | 2015-07-03 10:00 | 2015-07-03 16:00 | 50FF | Puneet
Auto Scheduled | 6.13 | Training to Viabhav,Navneet,Rajiv,Puneet,Jithin,Vishnu - Docker with Jenkins operations | 5 hrs | 2015-07-03 10:00 | 2015-07-03 16:00 | 50FF | Jithin
Auto Scheduled | 6.14 | integration of docker with artifactory- Will assist | 8 hrs | 2015-07-14 10:00 | 2015-07-15 12:00 | 37 | Rajiv
Auto Scheduled | 6.15 | integration of docker with artifactory- For Frontend | 8 hrs | 2015-07-14 10:00 | 2015-07-15 12:00 | 57FF | Jithin
Auto Scheduled | 6.16 | integration of docker with artifactory- For Backend | 8 hrs | 2015-07-14 10:00 | 2015-07-15 12:00 | 57FF | Puneet
Auto Scheduled | 6.17 | commiting docker images on each push complete- For Frontend | 5 hrs | 2015-07-15 12:00 | 2015-07-16 11:00 | 59 | Jithin
Auto Scheduled | 6.18 | commiting docker images on each push complete- For Backend | 5 hrs | 2015-07-15 12:00 | 2015-07-16 11:00 | 60SS | Puneet
Auto Scheduled | 6.19 | commiting docker images on each push complete- Will assist all | 5 hrs | 2015-07-15 12:00 | 2015-07-16 11:00 | 60SS | Rajiv
Auto Scheduled | 6.2 | pushing docker images to local repo-For Frontend | 4 hrs | 2015-07-16 11:00 | 2015-07-16 16:00 | 62 | Jithin
Auto Scheduled | 6.21 | pushing docker images to local repo-For backend | 4 hrs | 2015-07-16 11:00 | 2015-07-16 16:00 | 63FF | Puneet
Auto Scheduled | 6.22 | pushing docker images to local repo | 4 hrs | 2015-07-16 11:00 | 2015-07-16 16:00 | 63FF | Rajiv
Auto Scheduled | 6.23 | Milestone : Commiting docker container & push to artifactory | 0 days | 2015-07-16 16:00 | 2015-07-16 16:00 | 65
Auto Scheduled | 7 | 7. Integration of all work items for deployment automation - internal review | 2.13 days | 2015-07-23 11:00 | 2015-07-27 17:00
Auto Scheduled | 7.1 | Integration of all work items for deployment automation - internal review | 12 hrs | 2015-07-23 11:00 | 2015-07-27 17:00 | 20 | Bama
Auto Scheduled | 7.2 | Integration of all work items for deployment automation - internal review | 12 hrs | 2015-07-23 11:00 | 2015-07-27 13:00 | 68SS | Vaibhav
Auto Scheduled | 7.3 | Integration of all work items for deployment automation - internal review | 12 hrs | 2015-07-23 11:00 | 2015-07-27 11:00 | 68SS | Navneet
Auto Scheduled | 7.4 | Integration of all work items for deployment automation - internal review | 12 hrs | 2015-07-23 11:00 | 2015-07-27 11:00 | 68SS | Puneet
Auto Scheduled | 7.5 | Integration of all work items for deployment automation - internal review | 12 hrs | 2015-07-23 11:00 | 2015-07-27 13:00 | 68SS | Vishnu
Auto Scheduled | 7.6 | Integration of all work items for deployment automation - internal review | 12 hrs | 2015-07-23 11:00 | 2015-07-27 11:00 | 68SS | Jithin
Auto Scheduled | 7.7 | Milestone : Sucessfull POC completion | 0 days | 2015-07-27 11:00 | 2015-07-27 11:00 | 73
Auto Scheduled | 8 | 8. Actual implementation at project team QA server. | 3.88 days | 2015-07-30 14:00 | 2015-08-06 15:00
Auto Scheduled | 8.1 | Implement req. 2,3,4,5,3,6 | 16 hrs | 2015-07-30 14:00 | 2015-08-04 15:00 | 48 | Bama
Auto Scheduled | 8.2 | Implement req. 2,3,4,5,3,6 | 16 hrs | 2015-07-31 10:00 | 2015-08-04 15:00 | 76FF | Vishnu
Auto Scheduled | 8.3 | Implement req. 2,3,4,5,3,6 | 16 hrs | 2015-08-04 10:00 | 2015-08-06 15:00 | 76SS | Rajiv
Auto Scheduled | 8.4 | Milestone : Implementation compete- client end | 0 days | 2015-08-06 15:00 | 2015-08-06 15:00 | 78
Auto Scheduled | 9 | 9. Walkthrough of deployment automation process | 0.5 days | 2015-08-06 15:00 | 2015-08-07 12:00
Auto Scheduled | 9.1 | Walkthrough of deployment automation process | 4 hrs | 2015-08-06 15:00 | 2015-08-07 12:00 | 79 | Bama
Auto Scheduled | 9.2 | Walkthrough of deployment automation process | 4 hrs | 2015-08-06 15:00 | 2015-08-07 12:00 | 81FF | Vishnu
Auto Scheduled | 10 | 10. Documentation | 0.38 days | 2015-06-25 10:00 | 2015-06-25 13:00
Auto Scheduled | 10.1 | Deployment automation workflow. | 3 hrs | 2015-06-25 10:00 | 2015-06-25 13:00 |  | Vijeta
Auto Scheduled | 11 | 11. Project closure | 0.25 days | 2015-08-07 12:00 | 2015-08-07 15:00
Auto Scheduled | 11.1 | Closure activity | 2 hrs | 2015-08-07 12:00 | 2015-08-07 15:00 | 82 | Varghese